## Sheet1
Six-Sigma Project Charter
Project Title:Reduction of rejection DPMO from 2347 to 25 (target is 98.9% reduction) | Location: At Process PSR-1
Project Leader:Mr.SGP | Team Members:Mr. SP, Mr. JN, Mr.PQ, Mr.NR
Problem Statement: | Project Goal:
What:High rejection of part PT-1 of DPMO 2347 | 98% reduction of monthly DPMO. Current Sigma level = 4.0 Target Sigma Level = 5.56
Where: At process PRS-1
When:During manufacturing of part PT-1.
Who:Machine workforce. | Scope:
Why:Reason unknown | Included Process PRS-1
How often:Monthly | Project Plan:
How much:DPMO 2347 per month. |  | Target Date | Actual Date
Estimated Benefits (Business Case): | Define Phase | dd/mm/yy
Tangible Benefits:60 lakhs/ Annum cost saving. | Measure Phase | dd/mm/yy
| Analyze Phase | dd/mm/yy
Intangible Benefits: | Improve Phase | dd/mm/yy
| Control Phase | dd/mm/yy
Prepared by:Mr. SGP | Approved by: Mr. PGS
techiequality.com